## Sheet2
Row Labels | Sum of Estimation (in minutes)
Database designer | 480
Programmer | 5155
Scrum master | 180
Scrum Master and UI Designer | 30
Scrum master, Database designer | 120
Scrum master, Database designer, System architect | 480
System Architect | 360
System architect and Programmer | 240
System architect, Programmer | 240
Tester | 1935
UI designer | 1130
(blank) | 10350
Grand Total | 20700

## Sheet1
Product Backlog
Product Backlog items | Story | Responsible person | Estimation (in minutes) | Priority
#REF! | Selecting theme | Scrum Master and UI Designer | 30 | 1
2 | Setting up cloud server | Scrum master | 180 | 1
3 | Setting up project environment | Programmer | 60 | 1
4 | Editing theme to match with project | UI designer | 120 | 1
5 | Designing system use case | Database designer | 300 | 1
6 | Setting up initial database | Database designer | 60 | 1
7 | Designing sequence diagram, class diagram | System Architect | 240 | 1
8 | Designing initial data model for user login | System architect | 60 | 1
9 | Integrating database with data model | System architect and Programmer | 120 | 1
10 | Setting up cloud and database security | Scrum master, Database designer | 120 | 1
11 | Setting up application security | System architect and Programmer | 120 | 1
12 | Designing Login page | UI designer | 60 | 1
13 | Making the log in functionality | Programmer | 180 | 1
14 | Testing Log in functionality for all users | Tester | 30 | 1
15 | Designing password reset pages | UI designer | 90 | 2
16 | Integrating password reset functionality | Programmer | 30 | 2
17 | Testing Password reset | Tester | 20 | 2
18 | Designing common tables | Scrum master, Database designer, System architect | 480 | 1
19 | Designing common data stores | System architect, Programmer | 240 | 1
20 | Designing "Set terms and conditions" page | UI designer | 60 | 1
21 | Developing set terms and conditions page in admin panel | Programmer | 60 | 1
22 | Testing set terms and conditions page in admin panel | Tester | 20 | 1
23 | Developing logout functionality | Programmer | 15 | 1
24 | Testing logout functionality | Tester | 15 | 1
25 | Designing UI for add tag and view all tags pages | UI designer | 60 | 1
26 | Making add tag and view all tags in QA Manager panel | Programmer | 180 | 1
27 | Testing add tag and view all tags in QA Manager panel | Tester | 30 | 1
28 | Designing page for posting new idea | UI designer | 45 | 1
29 | Making post new idea functionality in student panel | Programmer | 180 | 1
30 | Testing post new idea functionality in student panel | Tester | 30 | 1
31 | Integrating tag to post new idea | Programmer | 20 | 1
32 | Integration test for post new idea with tag, checking if tag can be deleted after having an idea | Tester | 30 | 1
33 | Fixing bug for delete tag after submitting idea | Programmer | 30 | 1
34 | Testing for overdated idea submission | Tester | 30 | 1
35 | Fixing bug for overdated idea submission | Programmer | 180 | 1
36 | Retesting overdated submission | Tester | 20 | 1
37 | Adding email notification functionality | Programmer | 30 | 1
38 | Testing email notification functionality | Tester | 20 | 1
39 | Designing timeline page | UI designer | 105 | 1
40 | Making Timeline page in student panel | Programmer | 480 | 1
41 | Adding pagination in student timeline | Programmer | 180 | 1
42 | Testing pagination | Tester | 180 | 1
43 | Fixing pagination issue | Programmer | 60 | 1
44 | Retesting pagination | Tester | 60 | 1
45 | Adding comment and anonymous comment functionality in student panel | Programmer | 240 | 1
46 | Testing comment, anonymous comment and overdated comment | Tester | 120 | 1
47 | Integrating email notification to author | Programmer | 20 | 1
48 | Testing email notification to author | Tester | 20 | 1
49 | Fixing issues of overdated comment | Programmer | 90 | 1
50 | Adding Thumb up and thumb down functionality in student panel | Programmer | 300 | 1
51 | Testing thumb up and thumb down functionality | Tester | 60 | 1
52 | Fixing thumb up and thumb down bugs | Programmer | 90 | 1
53 | Designing view full post page | UI designer | 60 | 1
54 | Adding view full post functionality in student panel | Programmer | 120 | 1
55 | Adding video previewer in student panel | Programmer | 420 | 2
56 | Testing video previewer in student panel | Tester | 20 | 2
57 | Adding other attachment section in student panel | Programmer | 60 | 1
58 | Testing other attachments section, trying to download attachment | Tester | 20 | 1
59 | Fixing issue for downloading other attachments | Programmer | 60 | 1
60 | Adding all ideas of same category section in student panel | Programmer | 30 | 2
61 | Counting and displaying thumbs up, thumbs down, total comments, total views and total seen by in student panel | Programmer | 90 | 1
62 | Integration test to thumb up, thumb down, total comments, total views, total seen by, read full post | Tester | 60 | 1
63 | Designing view all ideas page | UI designer | 30 | 1
64 | Making View all ideas in student panel by overriding the functionalities of timeline | Programmer | 180 | 1
65 | Testing view all ideas in student panel | Tester | 30 | 1
66 | Designing view profile page | UI designer | 30 | 2
67 | Adding view profile by overriding functionalities of timeline. | Programmer | 60 | 2
68 | Adding QA Coordinator timeline, post an idea | Programmer | 90 | 1
69 | Designing My department activity page, designing the report pages | UI designer | 120 | 1
70 | Adding My Department Activity page for reports in QA CO-ordinator | Programmer | 420 | 1
71 | Testing Reports | Tester | 240 | 1
72 | Fixing bug of most popular ideas, most commented ideas | Programmer | 90 | 1
73 | Designing view all ideas > My department ideas, staff ideas pages | UI designer | 60 | 1
74 | Adding View All ideas > My department and staff ideas by overriding All ideas from student | Programmer | 90 | 1
75 | Testing and reporting but for viewing permission management | Tester | 120 | 1
76 | Fixing bug of list of ideas viewing permission management | Programmer | 120 | 1
77 | Adding aditional database tables | Database designer | 120 | 2
78 | Adding aditional data models | System architect | 60 | 2
79 | Designing submit an issue page | UI designer | 50 | 2
80 | Submit an issue | Programmer | 90 | 2
81 | Testing issue submission functionality | Tester | 30 | 2
82 | Designing view all issues page for QA Coordinator | UI designer | 30 | 2
83 | Developing fucntionality for view all issues page | Programmer | 60 | 2
84 | Designing view all issues page for QA Manager | UI designer | 30 | 2
85 | Testing view all issues page in QA Manager | Tester | 30 | 2
86 | Developing fucntionality for view all issues page in QA Manager | Programmer | 30 | 2
87 | Developing functionality for Download archave | Programmer | 60 | 1
88 | Testing download archive | Tester | 10 | 1
89 | Fixing bug for download archive | Programmer | 60 | 1
90 | Designing notificaitons and announcements tabs | UI designer | 30 | 2
91 | Setting up notification and announcements for users | Programmer | 120 | 2
92 | Testing notifications and announcements | Tester | 120 | 2
93 | Designing Update profile page | UI designer | 60 | 2
94 | Developing Update profile information functionalities | Programmer | 120 | 2
95 | Testing update profile information | Tester | 30 | 2
96 | Developing functionality for last activity count | Programmer | 60 | 2
97 | Designing manage batch and manage department page | UI designer | 90 | 2
98 | Developing manage batch and manage department functionality | Programmer | 120 | 2
99 | Testing manage barch and manage department functionalities | Tester | 60 | 2
100 | Integrating manage manage barch and manage depaerment with manage tag | Programmer | 60 | 2
101 | Performing complete integration test, reporting issue of profile side navigation bar | Tester | 300 | 1
102 | Fixing bug for profile sidenav | Programmer | 120 | 1
103 | Performing complete integration test 2 | Tester | 180 | 1